## Project Gantt
part_id | stage | planned_start | planned_finish | actual_start | actual_finish | machine | supplier | status
P-001 | Cutting | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-05 | M-Mill-A | Internal stock | done
P-001 | Drilling | 2026-05-06 | 2026-05-07 | 2026-05-06 | 2026-05-07 | M-Mill-A | Internal stock | done
P-001 | Heat treatment | 2026-05-08 | 2026-05-12 | 2026-05-08 | 2026-05-12 | M-Furnace-1 | Internal stock | done
P-001 | CMM inspection | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | M-CMM-1 | Internal stock | done
P-002 | Cutting | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-05 | M-Mill-A | Internal stock | done
P-002 | Drilling | 2026-05-06 | 2026-05-07 | 2026-05-06 | 2026-05-07 | M-Mill-A | Internal stock | done
P-002 | Shot peening (outsourced) | 2026-05-08 | 2026-05-15 | 2026-05-15 | 2026-05-22 | M-EXT-Hungary | ShotpinHU GmbH | delayed (supplier 7 days late)
P-002 | CMM inspection | 2026-05-16 | 2026-05-16 |  |  | M-CMM-1 | Internal stock | blocked (waiting for upstream)
P-003 | Cutting | 2026-05-04 | 2026-05-06 | 2026-05-04 | 2026-05-06 | M-Mill-B | Internal stock | done
P-003 | Drilling | 2026-05-07 | 2026-05-09 | 2026-05-07 | 2026-05-09 | M-Mill-B | Internal stock | done
P-003 | Surface grind | 2026-05-10 | 2026-05-11 | 2026-05-10 | 2026-05-11 | M-Grind-1 | Internal stock | done
P-003 | CMM inspection | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | M-CMM-1 | Internal stock | done
P-004 | Cutting | 2026-05-06 | 2026-05-07 | 2026-05-06 | 2026-05-07 | M-Mill-B | Internal stock | done
P-004 | Drilling | 2026-05-08 | 2026-05-09 |  |  | M-Mill-B | Internal stock | planned (overlaps M-Mill-B with P-003 Drilling)
P-004 | Heat treatment | 2026-05-10 | 2026-05-14 |  |  | M-Furnace-1 | Internal stock | planned
P-004 | CMM inspection | 2026-05-15 | 2026-05-15 |  |  | M-CMM-1 | Internal stock | planned
P-005 | Cutting | 2026-05-08 | 2026-05-12 | 2026-05-08 | 2026-05-12 | M-Mill-A | Internal stock | done
P-005 | Drilling | 2026-05-11 | 2026-05-12 |  |  | M-Mill-A | Internal stock | planned (starts before Cutting predecessor finishes)
P-005 | CMM inspection | 2026-05-13 | 2026-05-13 |  |  | M-CMM-1 | Internal stock | planned
P-006 | Material delivery | 2026-05-04 | 2026-05-04 | 2026-05-12 | 2026-05-12 | M-RECV-Dock | TitanIT GmbH (Italy) | delayed (8 days late, cascades downstream)
P-006 | Cutting | 2026-05-05 | 2026-05-06 | 2026-05-13 | 2026-05-14 | M-Mill-B | Internal stock | delayed
P-006 | Drilling | 2026-05-07 | 2026-05-08 |  |  | M-Mill-B | Internal stock | planned (date NOT rebaselined despite upstream delay)
P-006 | CMM inspection | 2026-05-09 | 2026-05-09 |  |  | M-CMM-1 | Internal stock | planned (date NOT rebaselined despite upstream delay)

## Notes
Field | Description
scope | Synthetic Turbocam ZK.1-style timeline excerpt for testing AI-assisted scheduling-issue detection.
units | All dates are ISO YYYY-MM-DD. Empty actual_* cells mean the stage has not started yet.
legend | status field uses values: planned, done, delayed, blocked
disclaimer | Synthetic data; not derived from real Turbocam projects.