## Project Gantt
part_id | stage | planned_start | planned_finish | actual_start | actual_finish | machine | supplier | status
P-100 | Cutting | 2026-05-04 | 2026-05-05 | 2026-05-04 | 2026-05-05 | M-Mill-A | Internal stock | done
P-100 | Drilling | 2026-05-06 | 2026-05-07 | 2026-05-06 | 2026-05-07 | M-Mill-A | Internal stock | done
P-100 | Shot peening (outsourced) | 2026-05-08 | 2026-05-15 |  |  | M-EXT-Hungary | ShotpinHU GmbH | planned
P-100 | CMM inspection | 2026-05-16 | 2026-05-16 |  |  | M-CMM-1 | Internal stock | planned
P-101 | Cutting | 2026-05-04 | 2026-05-06 | 2026-05-04 | 2026-05-06 | M-Mill-B | Internal stock | done
P-101 | Drilling | 2026-05-07 | 2026-05-09 | 2026-05-07 | 2026-05-09 | M-Mill-B | Internal stock | done
P-101 | Surface grind | 2026-05-10 | 2026-05-11 |  |  | M-Grind-1 | Internal stock | planned
P-101 | CMM inspection | 2026-05-12 | 2026-05-12 |  |  | M-CMM-1 | Internal stock | planned